## Sheet1
Group Member | Timeslot | Work Discription | Plan for Next Week | Reference Link
Jiajing Sun | Week 11 & Week 12 | 1. Community Page Front-end | Test and debug the prototype. | https://github.com/deco3500-2017/Team-WeChat/blob/master/group_chat.html
|  | 2. Me Page Front-end | Document the design process of the front end pages, and the testing issues in the final documentation | https://github.com/deco3500-2017/Team-WeChat/blob/master/grouplist_care.html
|  | 3. Detail Pages |  | https://github.com/deco3500-2017/Team-WeChat/blob/master/joblist_care.html
Mengwei Lin | Week 11 & Week 12 | 1. Test Wireframe | Final Document | https://drive.google.com/drive/folders/0B-hdfz4e2ioRYVNicF9HS3VLdTg?usp=sharing
|  | 2. Design Alternative |  | https://drive.google.com/open?id=0B6lY9JarSd33SGYwRzF2U1J6ZU0
Sheng Jing | Week 11 & Week 12 | 1. Community Page Share/ Apply | Axure Prototype | joblist_care.html/grouplist_care.html
|  | 2. Me Page Vote/ Task check |  | group_chat.html
Di Wany | Week 11 & Week 12 | 1. Test Wireframe | Plan for Final User Testing | https://drive.google.com/open?id=0B6lY9JarSd33SGYwRzF2U1J6ZU0
2. Design Alternative
Xiaoyu Shang | Week 11 & Week 12 | 1. Final Document | Poster and Exhibition Preparation | https://docs.google.com/document/d/1Gb0z-hN_U2lLxLBtM5_qSGnhC7PWpl1fekGZ91NX-ZE/edit