## Sheet1
Group Member | Timeslot | Work Discription | Reference Link
Jiajing Sun | Week 4 & 5 | Background Investigation & Target Audience | https://github.com/deco3500-2017/Team-WeChat/blob/master/Documents/Requirements/Proposal.pdf
|  | Design and Carry out Survey | https://docs.google.com/forms/d/14cmdjO3oMz8Vvr8ucW_IJ22uRbpVXGw3dhlIWhotUVA/edit?usp=sharing
| Week 6 & 7 | Design Task flow | https://github.com/deco3500-2017/Team-WeChat/blob/master/Documents/Requirements/Use%20task%20flows.docx
|  | Define Pro foma test plan and task design | https://github.com/deco3500-2017/Team-WeChat/blob/master/Documents/Testing/Test%20Plan.pdf
| Week 8 & 9 | Design and Build Web Pages | https://github.com/deco3500-2017/Team-WeChat/blob/master/group_chat.html
| Week 10 & 11 | Redesign and Build Web Pages | https://github.com/deco3500-2017/Team-WeChat/blob/master/grouplist_care.html
https://github.com/deco3500-2017/Team-WeChat/blob/master/joblist_care.html
| Week 12 & 13 | Build and Test Web Pages | https://github.com/deco3500-2017/Team-WeChat/blob/master/owner_group_chat.html
|  | Deploy Final Prototype | https://github.com/deco3500-2017/Team-WeChat/blob/master/ownerjoblist.html
|  | Testing | https://s4443483-deco7180.uqcloud.net/deco7350/login_carer.html
Final Document
|  | Flyer and Promotion Material | https://github.com/deco3500-2017/Team-WeChat/blob/master/Documents/Promotion/Flyer.pdf
Sheng Jing | Week 4 & 5 | Define Project Plan | https://github.com/deco3500-2017/Team-WeChat/blob/master/Documents/Requirements/Proposal.pdf
| Week 6 & 7 | Lauch Survey
| Week 8 & 9 | Research for Technical Solution | https://github.com/deco3500-2017/Team-WeChat/blob/master/group_chat.html
|  | Design Testing Survey Question | https://docs.google.com/forms/d/1p5vLej_GFcCtl81-1PKS3BOEC-1DG4T9ZcSfLrR1z-0/edit?usp=sharing
| Week 10 & 11 | Build Web Functions | https://github.com/deco3500-2017/Team-WeChat/blob/master/group_chat.html
https://github.com/deco3500-2017/Team-WeChat/blob/master/grouplist_care.html
| Week 12 & 13 | Build Mockup Prototype | https://github.com/deco3500-2017/Team-WeChat/blob/master/login_carer.html
https://github.com/deco3500-2017/Team-WeChat/blob/master/owner_profile.html
Mengwei Lin | Week 4 & 5 | Design and Carry out Survey | https://docs.google.com/forms/d/17vHHSlm-R1REG0rxZJMPtn4QwbgbNsbU-jOLD14RMEs/edit?usp=sharing
|  | Survey & Evaluation | https://github.com/deco3500-2017/Team-WeChat/blob/master/Documents/Requirements/Proposal.pdf
| Week 6 & 7 | Design Application Wireframe (Owner) | https://github.com/deco3500-2017/Team-WeChat/tree/master/Documents/Interfaces
| Week 8 & 9 | Implement Low Fadility Prototype | https://github.com/deco3500-2017/Team-WeChat/tree/master/Documents/Low-fidelity%20Prototype
|  | Facilitate Testing | https://github.com/deco3500-2017/Team-WeChat/tree/master/Documents/Testing
| Week 10 & 11 | Redesign Software feature (add pages for wireframe) | https://github.com/deco3500-2017/Team-WeChat/tree/master/Documents/Interfaces
|  | Design Icons for Prototype | https://github.com/deco3500-2017/Team-WeChat/tree/master/images
| Week 12 & 13 | Design Mockup Interfaces | https://github.com/deco3500-2017/Team-WeChat/tree/master/Documents/Mockup
|  | Prototype testing | https://docs.google.com/forms/d/14cmdjO3oMz8Vvr8ucW_IJ22uRbpVXGw3dhlIWhotUVA/edit?usp=sharing
Final Document
Di Wang | Week 4 & 5 | Concept Description | https://github.com/deco3500-2017/Team-WeChat/blob/master/Documents/Requirements/Proposal.pdf
| Week 6 & 7 | Design Application Wireframe (Carer) | https://github.com/deco3500-2017/Team-WeChat/tree/master/Documents/Interfaces
|  | Build low fidality prototype | https://github.com/deco3500-2017/Team-WeChat/tree/master/Documents/Low-fidelity%20Prototype
| Week 8 & 9 | Redesign testing procedure | https://github.com/deco3500-2017/Team-WeChat/blob/master/Documents/Testing/Tasks%20for%20TestR1.docx
| Week 10 & 11 | Design Alternative | https://github.com/deco3500-2017/Team-WeChat/tree/master/Documents/Interfaces/Paper%20Prototype
| Week 12 & 13 | Design Mockup Interfaces for Owners | https://github.com/deco3500-2017/Team-WeChat/tree/master/Documents/Mockup
Xiaoyu Shang | Week 4 & 5 | Team Charter | https://github.com/deco3500-2017/Team-WeChat/blob/master/Documents/Requirements/Proposal.pdf
| Week 6 & 7 | Define test purpose and Scope
Week 8 & 9
| Week 10 & 11 | Test evaluation | https://docs.google.com/document/d/1Gb0z-hN_U2lLxLBtM5_qSGnhC7PWpl1fekGZ91NX-ZE/edit?usp=sharing
| Week 12 & 13 | Design final poster | https://github.com/deco3500-2017/Team-WeChat/blob/master/Documents/Project_poster.pdf